## Project Scope
SPEAR3 SSA Upgrade Project - Scope Description
1. PROJECT OBJECTIVE
Replace the existing single 1.2 MW klystron RF source at the SPEAR3 storage ring with a distributed
solid-state amplifier (SSA) system consisting of 16 x 65 kW modules
delivering approximately 1,040 kW total RF power at 476.3 MHz to four RF cavities.
A stand alone test station to fully evaluate the performance iterating the vendor on the design
This project directly improves reliability (no single-point klystron failure), maintainability
(hot-swappable SSA modules), and operational flexibility (graceful degradation with N-1 capability).
2. RELATED PROJECT (LLRF Upgrade — Independent, Separate Scope)
The LLRF upgrade project (separate scope, separately funded) is underway independently.
The LLRF upgrade modernizes the controls infrastructure from legacy VXI/PLC-5/SLC-500 to:
- Dimtel LLRF9 digital controllers (2 units, already procured)
- Allen-Bradley CompactLogix/ControlLogix PLCs
- EPICS-based supervisory control software
- Few in-house chassises
The SSA upgrade leverages shared hardware where practical but is not dependent on LLRF completion.
Meanwhile, the upgrade will need extra controls and modification of the upgraded LLRF control system.
3. SSA PROJECT SCOPE
3a. SSA RF Source (WBS 1.0)
- Procurement of 16 x 65 kW SSA modules + 2 hot-swap spares from R&K Company
- Design study, acceptance test protocol development, vendor collaboration
- SSA test stand setup and commissioning at Building 122
3b. RF Distribution & Combining (WBS 2.0)
- 4 x 4:1 coaxial combiners (6-1/8" inputs to WR2100 output)
- 4 independent WR2100 waveguide runs from SSA building to cavities
- 4 high-power circulators (250+ kW CW @ 476 MHz)
- RF loads, directional couplers, transitions, waveguide supports
3c. Control Electronics & Protection Systems (WBS 3.0)
- 2 more LLRF9 and reconfiguration for SSA based High power system
- NEW Interface Chassis design for SSA interlock topology
- RF MPS upgrade
- Waveform buffer system
- SSA module status monitoring (VSWR/power/temperature/fan/power supply ect)
- PPS REDESIGN for SSA
- NIP system (Non-Ionizing Protection)
3d. Software & Integration (WBS 4.0)
- EPICS IOC development for SSA modules, NIP, PPS
- State machine / EPICS Coordinator extension for SSA operations
- Operator interface panels (EDM/CSS)
- Commissioning tools and scripts
- Documentation and operator training
3e. Installation & Commissioning (WBS 5.0)
- SSA module installation (4 stations, 4 modules each)
- RF distribution installation (waveguide, combiners, circulators)
- Controls and cabling installation
- System integration testing
- Phased commissioning (per-station turn-on)
3f. Site Preparation & Removal (WBS 6.0)
- Existing klystron and waveguide removal
- Cable tray relocation for new waveguide routing
- Equipment relocation (transformers, panels, cabinets)
3g. SSA test station development - support a 32 kW SSA module test (WBS 7.0)
- Equipments: rf source, waveguide components, circulator, rf load
- Control software
- Infrastructure (LCW, electricity, HVAC,
3h. Infrastructure (WBS 8.0 - Included in SSA Project)
- 480 VAC distribution system (Substation 507 upgrade, 2.5-3 MVA transformer)
- Cooling water upgrade (~400 GPM LCW for SSA stations)
- Building extension and mezzanine (~636 + 300 sqft, two-story)
3i. Decommissioning — Existing RF Station (WBS 9.0)
- Klystron system removal (Marconi K3512S, 1.2 MW CW, with solenoid,)
- HVPS removal (2.5 MVA: SCR rectifier, oil-insulated 12.47 kV transformer, crowbar circuit)
- Waveguide network removal (WR2100 from klystron to tunnel, magic tee 4-way splitter on roof)
- Circulator and RF loads removal, HCW cooling system drain/flush
- Lead shielding removal and hazardous waste abatement (EPA/RCRA classified)
3j. Project Management (WBS 10.0)
- Technical program management (~0.5 FTE/yr over ~5-year project)
- Safety reviews and PPS/NIP coordination with SLAC AD Safety Division
- Project management office support (~0.5 FTE/yr over ~ 5 year project)
4. KEY TECHNICAL PARAMETERS
- Operating frequency: 476.3 MHz
- Total RF power: 16 x 65 kW = 1,040 kW
- RF cavities: 4 (SPEAR3 storage ring)
- SSA per cavity: 4 modules combined via 4:1 combiner
- Waveguide: WR2100 (lambda_g = 80.4 cm at 476.3 MHz)
- Cooling: LCW, 400 GPM total (~100 GPM/station, deltaT ~10K)
- SSA building: two-story, ~936 sqft total, 27 ft height, 12 ft clear under platform
5. PROJECT TIMELINE (ESTIMATED)
- Overall: ~5 years, completion ~2032-2033
- Strongly dependent on Substation 507 upgrade schedule
- Facility support on LCW
- Facility design/construction constrained by engineering resources
- Vendor manufacturability
- Integration testing limited to SPEAR summer shutdown windows (~8 weeks)

## Class 4 Estimate
SPEAR3 SSA Upgrade Project - Class 4 Cost Estimate (AACE 18R-97)
Design Maturity: 5-15% ¦ Labor: $200/hr burdened ¦ 1 FTE=1,740 hrs/yr ¦ All costs in k$ ¦ Base year: 2026
NOTE: This estimate covers SSA upgrade scope including infrastructure and decommissioning (WBS 1-9). The LLRF upgrade is a separate, independent project with no dependency relationship.
WBS | Description | M&S (k$) | Labor (FTE) | Labor (k$) | Total (k$) | Conf. | Basis of Estimate / Notes
1.0 | SSA RF SOURCE
1.1 | SSA Modules (16 x 65 kW) | 4985.6 |  |  | 4985.6 | H | R&K quote July 2025: $311,600/unit x 16. 476.3 MHz CW.
1.2 | SSA Spare Modules (1 hot-swap) | 311.6 |  |  | 623.2 | H | 2 spares @ $311,600 each. Industry practice for 16-module system. Enables rapid replacement without vendor lead time.
1.3 | SSA Design Study & Prototype Test |  | 1 | 348 | 348 | M | 0.5 FTE prototype design/acceptance protocol + 0.5 FTE vendor collaboration & test iteration.
1.4 | SSA Test Stand (Bldg 122) | 75 | 0.5 | 174 | 249 | M | RF load (50 kW CW), power measurement, 480V service, LCW (~15 GPM). Existing Bldg 122 LCW connection usable (per 3/10 mtg).
| Subtotal WBS 1.0 | 5372.2 |  | 522 | 6205.8
2.0 | RF DISTRIBUTION & COMBINING
2.1 | 6-1/8" Coaxial Combiners (4 x 4:1) | 160 | 0.25 | 87 | 247 | M | 4 combiners, each combining 4 SSA outputs (6-1/8" coax) into WR2100. ~$40k each. See Ref Pricing tab for vendor links.
2.2 | WR2100 Waveguide Runs (4 independent) | 300 | 0.5 | 174 | 474 | M | 4 runs from SSA bldg to 4 cavities. Straights, bends, flex sections. ~10 lb/ft, hangers every 8 ft. Lambda_g=80.4 cm. Mega Industries/Space Machine vendors.
2.3 | Circulators (4 x 250+ kW @ 476 MHz) | 400 | 0.15 | 52.2 | 452.2 | L | 4 ferrite circulators. $80-120k each NEW (AFT Microwave, Mega Industries). PEP-II 1.5 MW units available (per 2/24 mtg) - if reusable, saves ~$400k.
2.4 | RF Loads (circulator loads, terminations) | 80 |  |  | 80 | M | 4 water-cooled circulator loads (~250 kW each), waveguide terminations. HCW-cooled (separate from SSA LCW per 3/10 mtg).
2.5 | Directional Couplers & Transitions | 60 |  |  | 60 | M | Directional couplers at combined outputs (4), WR2100-to-coax transitions, phase trimmers for combining efficiency. See Ref Pricing tab.
2.6 | Waveguide Supports, Hangers, Hardware | 50 | 0.25 | 87 | 137 | M | Unistrut, beam clamps, hangers every 8 ft. Some supports from platform structure above (per 3/10 mtg).
| Subtotal WBS 2.0 | 1050 |  | 400.2 | 1450.2
3.0 | CONTROL ELECTRONICS & PROTECTION SYSTEMS
3.1 | LLRF9 SSA Reconfiguration (4 units) | 20 | 0.5 | 174 | 194 | M | LLRF9 hardware installed during LLRF upgrade (no new purchase). SSA reconfiguration: new vector sum for 4-module combining, interlock remapping, firmware update. $20k for Dimtel support/firmware license. 0.5 FTE integration labor.
3.2 | Interface Chassis (NEW for SSA topology) | 30 | 1 | 348 | 378 | M | New design required: SSA topology fundamentally different from klystron. Per-station permit logic, 16-module status aggregation, SSA-specific interlock sequencing. PCB design + fab + chassis. CRITICAL PATH.
3.3 | RF MPS Upgrade (SSA topology) | 35 | 0.75 | 261 | 296 | M | Upgrade ControlLogix MPS for 16-module fault detection: individual module trip/bypass, graceful degradation (N-1 operation), new I/O cards for expanded inputs. AB PLC ~$22k + $13k additional I/O modules.
3.4 | Arc Detection System (carried over) | 20 | 0.3 | 104.4 | 124.4 | H | Microstep-MIS: sensors 470EUR x10, receivers 635EUR x6, cables, adapters. Same scope as LLRF upgrade. Per TaskListRev3 quote (Erik Bystricky Nov 2024). No change for SSA.
3.5 | Waveform Buffer System (reuse from LLRF) | 5 | 0.15 | 52.2 | 57.2 | H | Reuse waveform buffer installed during LLRF upgrade. Minimal SSA adaptation: reconfigure channel assignments for SSA monitoring points. $5k for any additional detectors/cables.
3.6 | SSA Module Status Monitoring | 15 | 0.25 | 87 | 102 | M | Per-module monitoring: VSWR, output power, temperature, fault status x16 modules. Ethernet/serial polling + analog readback. New for SSA.
3.7 | Tuner Motor Controllers (carried over) | 5 | 0.1 | 34.8 | 39.8 | H | Galil DMC-4143 controllers installed during LLRF upgrade. Cavity-side hardware, independent of RF source type. Minimal reconfiguration for SSA. $5k for spare parts/cables.
3.8 | PPS Redesign for SSA | 15 | 0.75 | 261 | 276 | M | Redesign required: HVPS contactor/grounding switch eliminated. New SSA PPS chain: 16x 480V SSA power permits, building access interlocks, emergency stop integration. Requires SLAC AD Safety Division review, RSWCF, formal change control.
3.9 | NIP System (Non-Ionizing Protection) | 60 | 0.75 | 261 | 321 | L | NEW: Required per SLAC ESH Ch.50 for 1,040 kW RF in new SSA building. RF field monitors/sensors ($15-25k), door interlocks ($10-15k), warning beacons/signage ($5k), interlock controller ($10-15k). 0.75 FTE: hazard analysis, RFSP development, safety review, documentation.
3.10 | Cables, Connectors, Integration Materials | 50 |  |  | 50 | M | RF cables (SMA, Type-N), fiber optic links, LEMO interlock cables, Ethernet, 480V power cables to SSAs, rack hardware, PDUs. Higher than LLRF upgrade due to 16 distributed modules.
| Subtotal WBS 3.0 | 255 |  | 1583.4 | 1838.4
4.0 | SOFTWARE & INTEGRATION
4.1 | EPICS IOC Development (SSA-specific) | 10 | 0.75 | 261 | 271 | M | SSA module IOCs (ASYN/StreamDevice for R&K Ethernet/serial), NIP system IOC, PPS status IOC. LLRF9 IOC carries over from LLRF upgrade. SSA-specific customization.
4.2 | State Machine / EPICS Coordinator (SSA) |  | 1 | 348 | 348 | M | Extend LLRF coordinator for SSA: module startup/shutdown sequencing, hot-swap logic, graceful degradation (N-1 mode), per-station state machine. CRITICAL: largest untouched software scope.
4.3 | Operator Interface (EDM/CSS Panels) |  | 0.25 | 87 | 87 | M | New displays: per-module SSA status, combining efficiency, NIP status, 16-channel fault tree. Extend existing panels from LLRF upgrade.
4.4 | Commissioning Tools & Scripts | 5 | 0.25 | 87 | 92 | M | SSA phase calibration, combiner efficiency optimization, module acceptance test scripts, fault injection testing.
4.5 | Documentation & Training |  | 0.25 | 87 | 87 | M | SSA system docs, NIP RFSP documentation, as-builts, operator training on SSA operations & module replacement.
| Subtotal WBS 4.0 | 15 |  | 870 | 885
5.0 | INSTALLATION & COMMISSIONING
5.1 | SSA Module Installation (4 stations) | 50 | 1.38 | 480 | 530 | M | 4 person x 3 weeks/station x 4 stations. Rack mounting, 480V power, LCW plumbing, RF cabling, control/interlock wiring. Per cover page row 8.
5.2 | RF Distribution Installation | 30 | 0.75 | 261 | 291 | M | Waveguide assembly, circulator installation (vertical per 2/24 mtg), combiner hookup, load installation. Crane required for heavy components.
5.3 | Controls & Cabling Installation | 20 | 0.5 | 174 | 194 | M | MPS rewiring, Interface Chassis install, NIP sensor installation, interlock cabling, Ethernet network for 16 SSA modules.
5.4 | System Integration Testing |  | 0.5 | 174 | 174 | M | End-to-end interlock testing, NIP verification, EPICS PV verification, fault injection. Limited window due to SPEAR operations.
5.5 | Phased Commissioning (per-station) | 20 | 0.69 | 240 | 260 | M | 6 person x 2 months commissioning. Incremental per-station power ramp. Performance: amplitude <0.1%, phase <0.1 deg.
| Subtotal WBS 5.0 | 120 |  | 1329 | 1449
6.0 | SITE PREPARATION & REMOVAL
6.1 | Existing Klystron/Waveguide Removal | 5 | 0.12 | 41.8 | 46.8 | H | Remove klystron, existing waveguide, magic tee splitters. Roof splitters removed; replaced by direct SSA-to-cavity runs (per 2/24 mtg).
6.2 | Cable Tray Relocation | 10 | 0.25 | 87 | 97 | M | Straighten S-shaped cable trays on roof (per 2/24 mtg). Relocate trays between 118 and ring ~10 ft outward.
6.3 | Equipment Relocation | 15 | 0.25 | 87 | 102 | M | Relocate transformers (2-3), panels, controls cabinets during downtime. Remove old air-handler/chiller behind 507 (per 2/24 mtg).
| Subtotal WBS 6.0 | 30 |  | 215.8 | 245.8
7.0 | PROJECT MANAGEMENT
7.1 | Technical Program Management | 20 | 2.5 | 870 | 890 | M | ~0.5 FTE/yr over ~5-year project. Schedule, resource, vendor management (R&K, Dimtel). M&S for travel, DOE reviews.
7.2 | Safety Reviews & PPS/NIP Coordination | 10 | 0.5 | 174 | 184 | M | PPS + NIP review/approval with SLAC AD Safety Division. LOTO, arc flash, OSHA compliance. RSWCF, RFSP documentation.
| Subtotal WBS 7.0 | 30 |  | 1044 | 1074
8.0 | INFRASTRUCTURE (Included in SSA Project Scope)
8.1 | 480 VAC Distribution System | 900 | 2 | 696 | 1596 | L | Sub 507 option ($1-2M per 1/27 mtg). 2.5-3 MVA transformer, 12kV feed, 480V panels for 16 SSAs. Alt: Sub 502 = $8-9M.
8.2 | Cooling Water (LCW/HCW) | 250 | 1.5 | 522 | 772 | L | 400 GPM LCW for 4 SSA stations. Option B: new 6"+ connection (per 3/10 mtg). Summer shutdown required.
8.3 | Building Extension & Mezzanine | 500 | 2 | 696 | 1196 | L | ~636 sqft + ~300 sqft mezzanine @ 27 ft. Two-story layout (per 2/24 mtg). OSHA stairway. Roll-up doors. Seismic. F&O prior estimate $1.3M.
| Subtotal WBS 8.0 (Infrastructure) | 1650 |  | 1914 | 3564
9.0 | DECOMMISSIONING — EXISTING RF STATION
9.1 | Klystron Removal & Disposal | 15 | 0.25 | 87 | 102 | M | Remove Marconi K3512S 1.2 MW klystron (~8-10 tons with solenoid). LOTO, de-energize RF, disconnect WR2100 waveguide, LCW cooling, HV connections. Crane lift from klystron room. Disposal per SLAC waste procedures.
9.2 | HVPS/Modulator Removal & Oil Disposal | 20 | 0.25 | 87 | 107 | M | Remove 2.5 MVA HVPS: SCR-controlled rectifier, 12.47 kV transformer (oil-insulated), crowbar circuit, HV bus. Drain/dispose transformer oil (~300-500 gal, test for PCBs). Disconnect 12.47 kV primary feed. Crane required for transformer (~5-10 tons).
9.3 | Waveguide Network & Magic Tee Removal | 10 | 0.15 | 52.2 | 62.2 | M | Remove existing WR2100 waveguide from klystron to tunnel roof. Depressurize dry-air system. Remove magic tee 4-way splitter on roof (per 2/24 mtg: roof splitters removed). Disassemble flanged connections, lower sections. ~10 lb/ft waveguide.
9.4 | Circulator, RF Loads & Ancillary Components | 5 | 0.1 | 34.8 | 39.8 | M | Remove existing AFT circulator (high-power ferrite, ~1-2 tons), HCW-cooled magic loads, circulator loads. Disconnect HCW cooling lines, drain/flush. Existing PEP-II circulators may be retained if usable for SSA (per 2/24 mtg).
9.5 | Lead Shielding Removal & Hazmat Abatement | 25 | 0.1 | 34.8 | 59.8 | L | Remove lead shielding around klystron/HVPS area. Lead is classified hazardous waste (EPA/RCRA). Requires certified hazmat crew. Radiological survey of klystron area for activation products (per SLAC RP procedures). M&S for disposal containers, transport.
9.6 | Crane/Rigging Services & Environmental Compliance | 50 | 0.1 | 34.8 | 84.8 | M | Crane rental (100-ton, ~$5-15k/day for 3-5 days) for klystron, HVPS transformer, heavy waveguide. Rigging contractor. PCB testing of transformer oil. Radiological clearance survey. Environmental compliance documentation per SLAC ES&H. Waste manifests.
| Subtotal WBS 9.0 (Decommissioning) | 125 |  | 330.6 | 455.6
| RF/CONTROLS SCOPE (WBS 1-7) | 6872.2 |  | 5964.4 | 13148.2
| INFRASTRUCTURE SCOPE (WBS 8) | 1650 |  | 1914 | 3564
| DECOMMISSIONING SCOPE (WBS 9) | 125 |  | 330.6 | 455.6
| PROJECT BASE ESTIMATE (WBS 1-9) | 8647.2 |  | 8209 | 17167.8
| CONTINGENCY (30% of base, per DOE 413.3B / AACE Class 4) |  |  |  | 5150.34 |  | AACE 18R-97 Class 4: -15% to +30% accuracy. DOE 413.3B requires contingency at conceptual design.
| TOTAL ESTIMATED COST (Base + Contingency) |  |  |  | 22318.14
KEY ASSUMPTIONS
A1 | Electrical based on Substation 507 option. Substation 502 would add ~$7M to WBS 8.1.
A2 | Circulator cost assumes new procurement ($400k). PEP-II 1.5 MW circulators may be reusable (saves ~$400k).
A3 | 2 SSA hot-swap spares included ($623k). Could reduce to 1 (saves $312k) or increase per ops.
A4 | Labor rate: $200/hr burdened (SLAC overhead-inclusive). 1 FTE = 1,740 hrs/yr.
A5 | LLRF upgrade is a separate, independent project (not a prerequisite). LLRF9 controllers, arc detection, waveform buffer, and tuner controllers carry over to SSA scope.
A6 | NIP system required per SLAC ESH Chapter 50 for new SSA building with >1 kW RF sources.
A7 | Decommissioning scope: Marconi K3512S klystron, 2.5 MVA HVPS (oil-insulated transformer, SCR rectifier, crowbar), AFT circulator, WR2100 waveguide/magic tee, lead shielding, HCW cooling. Per SLAC-PUB-10983.
A8 | HVPS transformer oil assumed non-PCB. PCB testing required prior to disposal (pre-1979 oil would increase cost significantly).
A9 | Scrap/salvage value of removed equipment not credited (conservative). Some copper, lead, steel may have modest scrap value.
KEY RISKS
R1 | Interface Chassis on critical path (new SSA-specific design not started). PCB iteration may add 3-6 months.
R2 | PPS redesign scope uncertain. 16-channel SSA safety chain more complex than single-klystron PPS. Safety review timeline unknown.
R3 | NIP system: first SSA installation at SPEAR. No prior RFSP template for this SSA configuration. Safety review may be lengthy.
R4 | EPICS Coordinator software largest untouched scope. Hot-swap logic and N-1 degradation are new SSA-specific requirements.
R5 | DOE lab construction costs typically 50-100% higher than commercial. WBS 8.3 building estimate based on F&O prior study ($1.3M); actual cost TBD per CD-1 design.
R6 | Limited SPEAR testing windows. Integration constrained to summer shutdowns and brief maintenance periods.
R7 | Decommissioning: HVPS transformer oil may contain PCBs (pre-1979 equipment from PEP-II era). PCB disposal costs could be 3-5x non-PCB estimate.
R8 | Decommissioning: Radiological activation of klystron/shielding requires RP survey. If contamination found, disposal costs increase substantially.

## Reference Pricing
SPEAR3 SSA Upgrade - Reference Pricing & Vendor Links
For procurement planning. Prices are indicative; formal quotes required before purchase.
Component | Vendor | URL / Product Link | Model / Part # | Unit Price | Date / Source | Notes
WBS 1.0 - SSA RF SOURCE
65 kW SSA Module (476.3 MHz CW) | R&K Company (Japan) | https://www.rk-microwave.com/ | Custom 65 kW SSA | $311,600 | July 2025 quote | Includes internal 480V PS, LCW cooling, VSWR protection, Ethernet/serial control
SSA RF Dummy Load (250 kW CW, water-cooled) | Ferrite Microwave Technologies (FMT) | https://ferriteinc.com/high-power-waveguide-terminations/water-cooled-loads/ | Custom WR2100 water-cooled load | $10-25k est. | Vendor catalog (verified) | FMT: WR28-WR2300 waveguide loads, 50 MHz-50 GHz. MIL-D-3954 compliant. Ultra-high temp refractory ceramic absorber. REPLACES Bird Technologies (max 20 kW, unsuitable).
WBS 2.0 - RF DISTRIBUTION & COMBINING
WR2100 Waveguide (straight, bends, flex) | Mega Industries | https://www.megaind.com/products/waveguide-sizes/wr2100-waveguide/ | WR2100 (21x10.5 in) | $50-150/ft est. | Catalog | 0.35-0.53 GHz, 205-290 MW peak rating, 0.188" wall. Also: Space Machine (space-machine.com)
WR2100 Waveguide (catalog/3D models) | Microwave Techniques (Mega subsidiary) | https://catalog.microwavetechniques.com/viewitems/by-waveguide-component-size/wr2100 | Various | RFQ | Catalog | Full 3D CAD catalog for WR2100 components: straights, bends, couplers, transitions, windows
WR2100 Directional Coupler | Mega Industries | https://www.megaind.com/products/waveguide-sizes/wr2100-waveguide/ | WR2100 coupler | $5-15k est. | Catalog | Various coupling ratios available. Also custom designs.
WR2100 Circulator (250+ kW CW @ 476 MHz) | Ferrite Microwave Technologies (FMT) | https://ferriteinc.com/high-power-microwave-circulators-isolators/waveguide-circulators/ | Custom WR2100 3-port circulator | $80-120k est. | Vendor inquiry (verified) | FMT: 1400+ circulator designs, WR28-WR2300, 50 MHz-50 GHz, 5W to 50+ MW. Scientific/accelerator specialist. AFT Microwave (aft-microwave.com) as alternate (L/S/C/X bands; confirm 476 MHz coverage before ordering).
WR2100 High-Power Water-Cooled Load (circulator termination) | Ferrite Microwave Technologies (FMT) / MCI Broadcast | https://ferriteinc.com/high-power-waveguide-terminations/water-cooled-loads/ | WR2100 water load, 250+ kW CW | $10-25k est. | Vendor catalog (verified) | For circulator port 3 termination. FMT water-cooled loads: refractory ceramic absorber, welded aluminum housing. MCI Broadcast (mcibroadcast.com) also makes accelerator-specific waveguide loads 0.32-10 GHz.
WR2100 Vacuum Window | Mega Industries | https://www.megaind.com/products/waveguide-sizes/wr2100-waveguide/ | WR2100 MegaSeal | RFQ | Catalog | If needed at waveguide-to-cavity interface
4:1 High-Power Waveguide Combiner (320 kW @ 476 MHz) | Mega Industries | https://www.megaind.com/high-power-waveguide-combiners-for-sspa/ | Custom WR2100 4:1 combiner (ref: WR1800 NSLS-II design) | $30-50k est. | Vendor reference (verified) | PRECEDENT: Mega built WR1800 4:1 combiner for NSLS-II at Brookhaven (500 MHz, 4×80kW=320kW, <0.12 dB loss, <1.18:1 VSWR). Nearly identical to SPEAR3 application (476 MHz, 4×65kW=260kW). REPLACES SPINNER Group (max 8.8 kW broadcast-grade, unsuitable).
WR2100-to-Coax Transition | Mega Industries / Made-in-China | https://www.megaind.com/products/waveguide-sizes/wr2100-waveguide/ | WR2100 transition | $500-5k | Catalog | WR2100 to 6-1/8" coax or N-type. Also: efinetech.en.made-in-china.com ($25-65 for adapter)
Unistrut Channel & Waveguide Hangers | Unistrut / Atkore | https://www.unistrut.us/ | P1000, P5500 series | $5-15/ft | Catalog | Standard Unistrut for waveguide support every 8 ft. WR2100 ~10 lb/ft.
WBS 3.0 - CONTROL ELECTRONICS & PROTECTION
Dimtel LLRF9/500 Controller | Dimtel, Inc. | https://www.dimtel.com/products/llrf9 | LLRF9/500 | $117,000 list | Vendor quote | 9-ch LLRF controller. 15% vol discount = $99,450. SSA project: reconfiguration only (hardware from LLRF upgrade)
Dimtel LLRF9/500 Specifications | Dimtel, Inc. | https://www.dimtel.com/products/specs/llrf9_500 | LLRF9/500 | See above | Spec sheet | 500 MHz center, 6 MHz BW, 9 RF inputs, FPGA interlocks, EPICS IOC built-in
AB CompactLogix Controller | Rockwell Automation | https://www.rockwellautomation.com/ | 5069-L320ER | $3,692 | TaskListRev3 | 2MB Ethernet controller. See IQElectro, IndustrialAutomationCo for distributor pricing.
AB Output Module (8-pt analog) | Rockwell Automation | https://www.rockwellautomation.com/ | 5069-OF8 | $1,536 | TaskListRev3 | Analog output. Qty 3 per MPS set = $4,607
AB Isolated Relay Output | Rockwell Automation | https://www.rockwellautomation.com/ | 5069-OX41 | $452 | TaskListRev3 | Qty 10 per MPS set = $4,516
AB Universal Analog Input | Rockwell Automation | https://www.rockwellautomation.com/ | 5069-IY4 | $521 | TaskListRev3 | Qty 2 per set = $1,043
AB Analog Input (8-ch) | Rockwell Automation | https://www.rockwellautomation.com/ | 5069-IF8 | $876 | TaskListRev3 | Qty 2 per set = $1,752
AB DC Input (16-pt) | Rockwell Automation | https://www.rockwellautomation.com/ | 5069-IB16 | $266 | TaskListRev3 | Qty 4 per set = $1,063
AB Spring RTB (18-pt) | Rockwell Automation | https://www.rockwellautomation.com/ | 5069-RTB18-SPRING | $62 | TaskListRev3 | Removable terminal blocks. Qty 25 = $1,561
Complete ControlLogix PLC Set | Rockwell Automation |  | See above BOM | $21,994/set | TaskListRev3 | Detailed BOM from LLRFUpgradeTaskListRev3.docx. SSA needs expanded I/O.
Galil 4-Axis Motion Controller | Galil Motion Control | https://www.galil.com/node/1486 | DMC-4143 | $1,675 | Galil website | 4-axis Ethernet/USB. 100-qty price: $1,115. For cavity tuner control.
Microstep-MIS Arc Sensor | MicroStep-MIS | https://microstep-mis.com/web/products?category=radiation+&product=waveguide_arc_detector | Optical sensor | 470 EUR ea | Nov 2024 quote | 10 sensors needed. Quote from Erik Bystricky.
Microstep-MIS Arc Receiver | MicroStep-MIS | https://microstep-mis.com/web/products?category=radiation+&product=waveguide_arc_detector | Process unit | 635 EUR ea | Nov 2024 quote | 6 receivers (5 active + 1 spare). Handles 2 sensors each.
Microstep-MIS Interconnect Cable (2m) | MicroStep-MIS | https://microstep-mis.com/ | Fiber cable | 186 EUR ea | Nov 2024 quote | 5 cables needed. Sensor-to-receiver connection.
MCL RF Power Detector | Mini-Circuits | https://www.minicircuits.com/ | ZX47-40LN-S+ | $105 ea | TaskListRev3 | Log detector for waveform buffer. 10 qty = $1,050. SMA connectors.
MCL SMA Adapter | Mini-Circuits | https://www.minicircuits.com/ | SF-SF50+ / NFFL-SF50+ | $6-30 ea | TaskListRev3 | SMA bulkhead adapters, N-to-SMA adapters
WBS 3.8-3.9 - SAFETY SYSTEMS (PPS, NIP)
RF Field Monitor / Sensor | Narda Safety Test Solutions | https://www.narda-sts.com/ | RadMan 2 / Area Monitor | $3-8k ea | Estimate | Personal/area RF exposure monitors. For NIP system per SLAC ESH Ch.50.
RF Safety Interlock Controller | Various / Custom |  | PLC-based or dedicated | $10-15k | Estimate | Door interlocks, emergency stops, RF enable/disable logic. May use AB CompactLogix.
RF Warning Beacons & Signage | Federal Signal / OSHA-compliant |  | Warning lights + signs | $2-5k | Estimate | SLAC ESH Ch.50 requires visible/audible warnings when RF active in accessible areas
SLAC ESH Chapter 50 (RF Safety) | SLAC ES&H Division | https://esh.slac.stanford.edu/hazardous_activities/rf | Reference | N/A | May 2024 | Program manager: Mike McDaniel. Governs all RF sources >1W at SLAC. IEEE C95.1 based.
OSHA 1910.97 (Nonionizing Radiation) | OSHA | https://www.osha.gov/laws-regs/regulations/standardnumber/1910/1910.97 | Reference | N/A | Federal reg | Federal standard for electromagnetic radiation exposure limits
VENDOR VERIFICATION NOTES (March 2026)
Bird Technologies | REMOVED — Max power 20 kW (8740 Series). Unsuitable for 250+ kW circulator loads. Replaced by FMT.
SPINNER Group | REMOVED — Broadcast-grade combiners (8.8 kW max @ 80.5 MHz). Unsuitable for 260 kW @ 476 MHz. Replaced by Mega Industries.
AFT Microwave | CAUTION — Products focus L/S/C/X bands (GHz range). Confirm 476 MHz coverage before ordering. FMT is preferred.
Ferrite Microwave Technologies (FMT) | ADDED — WR28-WR2300, 50 MHz-50 GHz, 1400+ designs. Accelerator specialist. Loads + circulators.
Mega Industries SSPA Combiner | ADDED — NSLS-II precedent: 4×80kW=320kW @ 500 MHz (Brookhaven). Nearly identical to SPEAR3.
MCI Broadcast | ADDED — Micro Communications waveguide loads for particle accelerators, 0.32-10 GHz.
All other vendors | VERIFIED — Links confirmed active, components confirmed suitable for 476.3 MHz / WR2100 / high-power CW.

## cover page
| The SSA upgrade project includes follow items |  |  |  |  | 1 FTE(hr)/yr | 1740
|  | M&S (k$) | Labor (hours) | lablor rate ($/hr) | labor (k$) | Total ($k) | Note
solid-state amplifier (SSA) system consisting of 16 x 65 kW modules | 1 MW SSA
| 16 of 65kW unit | 4.9856 |  |  |  | 4.9856 | based on one 65 kW unit quote from R&K in July 2025
A stand alone test station to fully evaluate the performance iterating the vendor on the design
| SSA design study |  | 1740 | 200 | 348 | 348 | 1) intial design 0.5 FTE for prototype, 2) 0.5 FTE for prototype test and design iteration with the vendor
| SSA installation and commissioning | 100 | 3840 | 200 | 768 | 868 | 1) MS for tools and parts; 2) 4 person-3 week per station for installation (12 person-month), 6 person-2-month for commissiong
| Existing waveguide remove and Cable tray relocation | 10 | 640 | 200 | 128 | 138 | 1) MS for the extra cable tray; 2) 4 person-1moth work
Control Electronics
| 4LLRF9 units | 398 | 870 | 200 | 174 | 572 | 4 × Dimtel LLRF9/500 @ $99.45k each (15% volume discount from $117k list); 0.5 FTE for integration & EPICS IOC configuration
The LLRF upgrade project (separate scope, separately funded) is underway independently. | MPS | 100 | 1740 | 200 | 348 | 448 | ControlLogix PLC hardware (~$22k/station × 4), interlock chassis, relay modules, arc detection sensors ($20k), and interface electronics; 1 FTE for design/assembly/testing
| software | 20 | 3480 | 200 | 696 | 716 | EPICS IOC development, state machine, fault handling, auto-recovery, operator EDM/CSS panels, MATLAB integration, SSA-specific commissioning tools; 2 FTE for development & commissioning
- Dimtel LLRF9 digital controllers (2 units, already procured)
| Waveguide runs | 1050 | 3480 | 200 | 696 | 1746 | 4 WR2100 waveguide runs to cavities (~$300k); 4 circulators 250kW@476MHz (~$400k); coaxial combiners 6-1/8" to WR2100 (~$200k); loads, transitions, supports/hangers (~$150k); 2 FTE design/install/test
| Circulators (4 × 250 kW) | [5 empty] | Existing PEP-II 1.5 MW circulators available (per 2/24 mtg notes) — if usable, saves ~$400k; alternative: smaller 250 kW units
- Few in-house chassises | WR2100 + 6-1/8" coaxial combiner | [5 empty] | Each SSA cabinet outputs 6-1/8" coax → 8:1 coaxial combiner → WR2100 to cavity; waveguide λg ≈ 80.4 cm at 476.3 MHz; lengths must match to ±nλg
The SSA upgrade leverages shared hardware where practical but is not dependent on LLRF completion. | Project management | 30 | 5220 | 200 | 1044 | 1074 | Project management, safety reviews (LOTO, OSHA), coordination with F&O, DOE reviews; ~0.5 FTE avg over 6-year project; M&S for travel/reviews/meetings
Meanwhile, the upgrade will need extra controls and modification of the upgraded LLRF control system.
3. SSA PROJECT SCOPE | 480 VAC Distribution System | 900 | 3480 | 200 | 696 | 1596 | Based on Substation 507 option ($1-2M per 1/27 mtg); 2.5-3 MVA transformer 12kV→480V outdoor (~$150-200k); 12kV feed from Bldg 507 + switchgear (~$300k); 480V distribution panels/breakers 4-8 buckets per SSA (~$200k); civil, cable, installation (~$200k); 2 FTE electrical engineering/oversight
| Transformer + 12kV feed | [5 empty] | Primary location: field near SPEAR tunnel entrance (per 2/24 mtg). 12kV from Bldg 507 → transformer → 480V back to SSA racks. Avoid reliance on Substation 502 (uncertain timeline)
| Cooling water | 250 | 2610 | 200 | 522 | 772 | 400 GPM LCW for 4 SSA stations (~100 GPM each, ΔT~10K); upgrade 4" to 6"+ piping ($100-150k); manifolds, valves, flow meters, controls ($50-75k); HCW for loads separate ($25-50k); 1.5 FTE plumbing design + install during summer shutdown
| LCW piping upgrade | [5 empty] | Option B preferred (new 6"+ connection to main header, per 3/10 mtg). Plumbing mods targeted for 2-month summer downtime. Javier to coordinate with F&O (Ota). Test lab Bldg 122 needs ~15 GPM separately.
| Infrastructure | 500 | 3480 | 200 | 696 | 1196 | New SSA building extension ~636 sqft + ~300 sqft mezzanine @ ~27 ft height; OSHA-compliant stairway (~25 risers + landing); roll-up door(s) for forklift/rack delivery; HVAC for SSA heat rejection; relocate condensing unit, panels, existing equipment
| Building extension + mezzanine | [5 empty] | Two-story SSA layout per 2/24 mtg. 9 ft clear height under platform. Structural: remove non-structural shed walls, add new column/I-beam. Seismic compliance. F&O prior estimate for test facility: $1.3M (per 1/27 mtg)
| Equipment relocation | [5 empty] | Remove old air-handler/chiller behind 507; relocate transformers (2-3), distribution panels, MPS controls cabinets during downtime; cable tray relocation ~10 ft outward between 118 and ring
| TOTALS | 3362.9856 | 30580 |  | 6116 | 9478.9856 | Sum of all line items (M&S + Labor)
| Total FTE-years |  | 17.5747 |  |  |  | Total labor expressed in FTE-years
| Contingency (not included) | [5 empty] | Recommend 25-35% contingency at conceptual design stage per DOE Order 413.3B. Applied to grand total, this would add ~$3-5M.
- 2 more LLRF9 and reconfiguration for SSA based High power system
- RF MPS upgrade | for 16-module fault detection and N-1 graceful degradation
- Waveform buffer system
- SSA module status monitoring (VSWR/power/temperature/fan/power supply ect) | upgrade or rebuild to include many more SSA rf channels
- PPS REDESIGN for SSA
- NIP system (Non-Ionizing Protection)
- Equipment relocation (transformers, panels, cabinets)
- Project management office support (~0.5 FTE/yr over ~ 5 year project)
- Klystron system removal (Marconi K3512S, 1.2 MW CW, with solenoid,)
- Lead shielding removal and hazardous waste abatement (EPA/RCRA classified)
3i. SSA test station development - support a 32 kW SSA module test
#NAME?
4a. Infrastructure (WBS 8.0 - Included in SSA Project)
- Cooling water upgrade (~400 GPM LCW for SSA stations)
- SSA per cavity: 4 modules combined via 4:1 combiner
- SSA building: two-story, ~936 sqft total, 27 ft height, 12 ft clear under platform
- Overall: ~5 years, completion ~2032-2033
- Facility support on LCW
- Integration testing limited to SPEAR summer shutdown windows (~8 weeks)

## SSA quote from R&K
k$
1 65 kw unit | 311.6
16 units | 4985.6