## Project Overview
SPEAR3 LLRF Upgrade — Project Schedule
SSRL / SLAC National Accelerator Laboratory — RF Department
Project | SPEAR3 Low-Level RF (LLRF) Upgrade
Document ID | SPEAR3-LLRF-PDR-001 Rev 1 ¦ Schedule Rev 1.0
Generated | April 16, 2026
Project Lead | Wang, Faya (fywang@slac.stanford.edu)
Tech Lead | Sebek, Jim (sebek@slac.stanford.edu)
Target | FY27 Commissioning — September 2027
Charge Code | 22884-A3010
Project Phases Summary
Phase | Name | Period | # Tasks
Phase 1 | Maximum Standalone Development | Now → Oct 2026 | 15
Phase 2 | Incremental Subsystem Integration | Aug → Dec 2026 | 8
Phase 3 | Critical Path Integration | Jan → Apr 2027 | 5
Phase 4 | Full Power Commissioning | Apr → Sep 2027 | 4
Status Legend
✅ Complete | Task is fully complete.
🟡 In Progress | Task is actively being worked on.
🔴 Not Started | Task has not yet begun.
⚠️ CRITICAL | Critical path item — delays impact commissioning date.

## Project Schedule
SPEAR3 LLRF Upgrade — Project Schedule
Generated: April 16, 2026 ¦ Target: FY27 Commissioning (September 2027) ¦ Charge Code: 22884-A3010
WBS | Task | Lead | Status | Target Date | Notes
PHASE 1 — Maximum Standalone Development ¦ Now → October 2026
1.1 | LLRF9 Units installed in B132 | Sebek, Jim | ✅ Complete | Apr 2026 | 2 units installed in Klystron Bldg 132
1.2 | Dmitry software upgrade (all 4 units) | Dunning, Michael | 🟡 In Progress | Apr 2026 | Dmitry visiting April to upgrade; incl. Bldg 15 units
1.3 | Motion control: B132 cavity test | Dunning, Michael | 🟡 In Progress | Apr 2026 | April downtime window; Galil controller with EPICS driver
1.4 | Waveform Buffer — integration ready | Zhang, Dehong | 🟡 In Progress | May 2026 | DAQ working; 200 kHz BW; EDM GUI functional
1.5 | Arc detector — procurement decision | Lion, Rob / Vedyanina, Kira | 🟡 In Progress | May 2026 | Awaiting updated MicroStep-MIS quote & STP files
1.6 | PLC programming environment setup | Larrus, Marc H. | 🔴 Not Started | May 2026 | New Rockwell machine + license needed
1.7 | RF MPS EPICS IOC development | Condamoor, Shantha | 🔴 Not Started | Jun 2026 | Depends on MPS PLC tag list availability
1.8 | HVPS PLC code (SLC-500 → CompactLogix) | Larrus, Marc H. | 🟡 In Progress | Jun 2026 | 95% complete; remaining: klystron cathode control
1.9 | TID SLA scope finalized | Condamoor, Shantha | 🟡 In Progress | May 2026 | SLA submitted; scope review meeting needed with Jim/Jing/Dehong
1.10 | Interface Chassis specification | Sebek, Jim | 🔴 Not Started | Jun 2026 | ⚠️ CRITICAL PATH — blocks all integration
1.11 | Interface Chassis PCB/chassis design | Sebek, Jim + Designer | 🔴 Not Started | Aug 2026 | ⚠️ CRITICAL PATH — no system integration without this
1.12 | PPS Interface Box design & fabrication | Morris, Ben | 🟡 In Progress | Jul 2026 | Design approach agreed (Bud box, 4 relays); needs SLAC AD Safety approval
1.13 | Test Stand 18 upgrade for HVPS controller | Larrus, Marc H. / Morris, Ben | 🔴 Not Started | Aug 2026 | Required before HVPS PLC commissioning on SPEAR
1.14 | Klystron heater: procure programmable AC supply | Morris, Ben | 🟡 In Progress | Jun 2026 | Chroma AC supply identified; tested & ready to proceed
1.15 | EPICS/Python coordinator framework | Condamoor, Shantha | 🔴 Not Started | Aug 2026 | ⚠️ CRITICAL PATH — largest untouched software scope (state machine, fault handling, UI)
PHASE 2 — Incremental Subsystem Integration ¦ August → December 2026
2.1 | Tuner Galil test on Booster cavities | Dunning, Michael | 🔴 Not Started | Aug 2026 | Test before committing to SPEAR storage ring (high-risk subsystem)
2.2 | HVPS PLC commissioning on Test Stand 18 | Larrus, Marc H. | 🔴 Not Started | Sep 2026 | Validate before installing on SPEAR3
2.3 | Arc detector adapters fabricated & installed (cavity) | Lion, Rob / Vedyanina, Kira | 🔴 Not Started | Aug–Sep 2026 | Summer downtime is primary installation window
2.4 | RF MPS integration: LLRF9 + waveform buffer + HVPS | Condamoor, Shantha | 🔴 Not Started | Oct 2026 | Requires Interface Chassis and PLC tag lists
2.5 | Interface Chassis fabrication | Designer (TBD) | 🔴 Not Started | Oct 2026 | Depends on PCB design completion (1.11)
2.6 | Interface Chassis bench testing | Sebek, Jim | 🔴 Not Started | Nov 2026 | Full interlock logic verification before SPEAR install
2.7 | PPS Interface Box installation + approval | Morris, Ben | 🔴 Not Started | Nov 2026 | Requires SLAC AD Safety Division review and sign-off
2.8 | Klystron heater integration with RF MPS | Morris, Ben / Larrus, Marc H. | 🔴 Not Started | Nov 2026 | Heater must be at operating temp before HVPS enable
PHASE 3 — Critical Path Integration ¦ January → April 2027
3.1 | LLRF9 vector sum + feedback loop verification (with RF) | Sebek, Jim | 🔴 Not Started | Jan 2027 | Verify 4-cavity feedback; tuner phase data at 10 Hz
3.2 | Full EPICS IOC integration (all subsystems) | Condamoor, Shantha | 🔴 Not Started | Feb 2027 | All PVs verified: LLRF9, HVPS, MPS, Motor, WFBuffer
3.3 | End-to-end interlock chain test (limited RF power) | Sebek, Jim | 🔴 Not Started | Mar 2027 | Full interlock chain: arc detect → Interface Chassis → HVPS
3.4 | Tuner control loop integration with LLRF9 | Dunning, Michael | 🔴 Not Started | Mar 2027 | Phase-based, 1 Hz; load angle offset loop
3.5 | Software state machine integration + fault handling | Condamoor, Shantha | 🔴 Not Started | Apr 2027 | States: OFF, TUNE, ON_CW, FAULT; auto-recovery
PHASE 4 — Full Power Commissioning ¦ April → September 2027
4.1 | Incremental RF power ramp | Sebek, Jim | 🔴 Not Started | Apr 2027 | Gradual increase; monitor all subsystems
4.2 | Performance validation (amplitude <0.1%, phase <0.1°) | Sebek, Jim / Wang, Faya | 🔴 Not Started | Jun 2027 | Must meet or exceed legacy SPEAR3 performance
4.3 | Operator training | All | 🔴 Not Started | Jul 2027 | New EPICS panels, state machine, fault procedures
4.4 | Final documentation + commissioning report | All | 🔴 Not Started | Sep 2027 | Complete documentation package; archive in shared folder

## Critical Risks
SPEAR3 LLRF Upgrade — Key Technical Risks
Source: SPEAR3-LLRF-PDR-001 Rev 1, Section 19.3 ¦ April 16, 2026
Risk Item | Risk Level | Impact / Consequence | Mitigation
Interface Chassis (design not started) | 🔴 CRITICAL | Blocks ALL system integration — no subsystem can be fully commissioned without it. | Start specification immediately; target completion Jun 2026. PCB design by Aug 2026.
EPICS/Python Coordinator software | 🔴 CRITICAL | Largest untouched software scope: state machine, fault handling, auto-recovery, operator UI. | Begin framework by Aug 2026 (Phase 1). Develop in parallel with hardware; use simulated interfaces.
Tuner motor controller reliability | 🔴 HIGH | Multiple previously tested candidates failed reliability requirements. Highest risk subsystem. | Test Galil DMC-4143 on Booster RF cavity first (Aug 2026) before SPEAR storage ring commitment.
PPS Interface Box approval delays | 🔴 HIGH | Requires SLAC AD Safety Division review + radiation safety verification — long lead time. | Engage protection group immediately. Use proven PPS design (identical to gallery baseline).
RF MPS PLC EPICS integration | 🔴 HIGH | Hardware assembled and tested standalone, but EPICS IOC, Interface Chassis integration, and reset sequencing not started. | Start IOC development Jun 2026. Requires MPS PLC tag list from Marc.
Arc detector adapter fabrication | 🟡 MEDIUM | Summer downtime (Aug–Sep 2026) is the primary window for cavity access. Missing it delays installation by ~1 year. | MicroStep-MIS quote decision by May 2026. Begin adapter design/fabrication no later than Jun 2026.
HVPS PLC code migration (SLC-500 → CompactLogix) | 🔴 HIGH | Legacy SLC-500 code must be reverse-engineered and rewritten. Risk of missed functionality. | Build and use Test Stand 18 (B44) for full commissioning before SPEAR install. Marc leads.