# LLRF Upgrade Task List

July 18, 2025

# Summary

- We have already procured the high cost items for the upgrade

- Can purchase another $50k or so this year with existing project funds (needs some engineering support for this)

- Future procurements will mainly be for components to build circuit boards and chassis.

- Major effort will be personnel

  - Mechanical support

  - Electrical support

    - Engineering to finish designs

    - Designer support to design and fabricate PCBs

    - Designer support to design and fabricate chassis

  - Documentation

    - Need coordinators to update existing documentation and create new documentation.

  - Software support

# System Overview – Main Components

## Low-Level RF Controls

- Heart of the LLRF system to stabilize the RF

- Monitors powers and signals from the klystron, cavities, and waveguides

- Maintains the total gap voltages and phases constant

- Must communicate with other parts of the RF system

  - Control system to receive general commands and setpoints

  - HVPS to tell the system status and set the correct HVPS output

  - Tuner controllers to keep the cavities tuned

- Must supply permits to

  - HVPS

- Must obtain permits from

  - PPS

  - SPEAR MPS

  - SPEAR orbit interlock

  - RF MPS

## Power Systems

### High Voltage Power Supply

- Intelligence to control the power supply, implement HVPS MPS, and communicate with the rest of the controls (Rockwell Automation/Allen-Bradley CompactLogix PLC)

- Commercial thyristor gate driver board (Enerpro)

- Analog interface between PLC and supply for both monitoring and control

- Communication with higher level LLRF controls

### Klystron

- Monitors for system MPS

## Machine Protection System

- Monitoring various power levels, voltages, currents, flows, temperatures, waveguide pressures, etc.

- Provides permit to both LLRF and HVPS

# Effort Required

## Design

### LLRF System

- Completely specified

### MPS System

- Completely specified

### HVPS Controller

- 75% specified based on existing system.

  - Redesign of analog regulator board to slightly modify and upgrade system to modern components.  (JS)

  - Re-specification of commercial gate firing board (Enerpro)  (JS)

  - Re-programming of PLC code with modern CompactLogix  (ML, BM)

  - Improvement of PPS interface  (ML, BM)

### Arc Detection Circuitry

- The current system does not work.

- A concept exists for a new design with commercial components.

- Details of mechanical interface to waveguides and cavities needs to be done

- Electrical interface chassis needs to be designed

### Slow Power Monitoring

- Existing LLRF has more “fast” RF channels than does Dimtel LLRF9

- Need about 8 channels for slow power monitoring (circulator reflected power, load reflected powers, etc.)

- Conceptual design to use Minicircuits power detectors and some analog signal processing with MPS trip levels

- Need to then digitize these signals to input into the control system

### Interface Chassis

- Interfaces specified for Dimtel LLRF9, but no design has started.

### Stepper Motor Controls for Cavity Tuners

- Existing controllers obsolete

- Have conceptual design for stepper motor controls but have not had resources or time to move this to production

- Require robust system that updates small steps at a 1 Hz rate

- Have been unable to prove reliability between controls and hardware systems we have tried.

- Will investigate motion control solutions developed by Domenico and Mike Dunning to see if they will work.

- (Outside scope of project is a better mechanical design of tuner motion that should be carried out.)

### Software

- Conceptual design based on reproducing functionality of existing system with a combination of Dimtel LLRF9, MPS, and PLC

- Nothing has been fleshed out.

## Procurement

### LLRF System

- Procurement complete

- LLRF9 with complete set of spares in house

### MPS System

- All PLC modules in house

- Could purchase several spare modules ($10k - $20k?)

### HVPS Controller

- All PLC modules in house for HVPS1, HVPS2, and B44 Test Stand (spare for operations)

- Need to procure Enerpro boards (3 operational and two spares ~$5k)

- Will have small costs (<$20k?) for power supplies, ICs, PC boards, etc., but detailed design needed before these can be purchased.

### Arc Detection Circuitry

- Microstep-MIS sells components for four cavities and klystron for about $10k

- Need mechanical design before we know which of their components will interface with our system

- Another ~$10k for our work to interface these units to our system

### Slow Power Monitoring

- 10 Minicircuit detectors for about $1100

- Design and build chassis $10k

### Interface Chassis

### Stepper Motor Controls for Cavity Tuners

- Will check cost with Domenico and Mike

### Software

Could spend about $50k this year for known components.  Rest of spending not large and likely can be spent from operational funds.

## Fabrication

### LLRF System

- None required

### MPS System

- Already complete

### HVPS Controller

- No progress

### Arc Detection Circuitry

- No progress

### Slow Power Monitoring

- No progress

### Interface Chassis

- No progress

### Stepper Motor Controls for Cavity Tuners

- Production chassis have been built.

- They have been used as prototypes for candidate controllers.

- Possibly can be used for Domenico’s design

- Otherwise work with Danh’s design

### Software

## Documentation

### LLRF System

- Dimtel’s documentation is complete

### MPS System

- Existing SPEAR3 documentation exists

- Mostly correct

- Needs to be upgraded to as built for some signals

- Reasonable effort required (~25 schematics?)

### HVPS Controller

- Existing SPEAR3 documentation exists

- Mostly correct

- Needs to be upgraded to as built for some signals and include upgraded parts of the system

- Reasonable effort required (~25 schematics?)

### Arc Detection Circuitry

- Documentation package must be created

### Slow Power Monitoring

- Documentation package must be created

### Interface Chassis

- Documentation package must be created

### Stepper Motor Controls for Cavity Tuners

- Documentation package must be created

### Software

- Documentation package must be created

## Software

## Commissioning

### LLRF System

- Prototype LLRF system commissioned on SPEAR3 before procurement

- Dimtel offers one week of commissioning assistance

### MPS System

- Rebuilt system tested on SPEAR3 with no RF power

- No issues found

- Remaining commissioning should go well

### HVPS Controller

- Intend to commission in Test Stand 18 in the Test Lab before installing in SPEAR

### Arc Detection Circuitry

### Slow Power Monitoring

### Interface Chassis

### Stepper Motor Controls for Cavity Tuners

- Could build prototype and test on Booster tuners to gauge robustness of system.

### Software

# LLRF Controls

We have purchased an LLRF9 control system from Dimtel.  Two LLRF9 units are required for operation.  We have purchased four units in order to have a complete set of spares.

## Interfaces

The rest of our control system will have one input into and one output interface with the LLRF9.

### Input

Our input will be a permit from the rest of the control system for the LLRF9 to produce an RF input to the drive amplifier.

### Output

The LLRF9 output will be a permit for our MPS system to tell us that the LLRF9 has detected a fault and has zeroed its input to the drive amplifier.

## Additional RF Monitoring

The LLRF9 monitors only 18 RF inputs.  We will want six more inputs from the current system and another RF input from the forward power to locally measure the klystron collector power for our MPS system.

A commercial product for this is the MCL ZX47-40LN-S+.  The cost for ten each is $104.76 each, so this purchase is $1050.  We will need SMA bulkhead adapters, MCL SF-SF50+, fourteen each at $6.45 each for a total of $100 for fifteen, or maybe seven Type N to SMA, NFFL-SF50+, at $29.90 each for a total of $210.  We will also need 14 SMA-SMA cables.  Wurth Elektronik 65503503530503 with SMA to SMA RG-174 cable is $13.60 each from Digikey for $200.  Mouser sells Amphenol CO-174SMAX200-1 for $12.42 each.  MCL 141-12SM+ are $15.71 each.  MCL FL141-12SM+ are $23.00 each.  The total hardware cost for this monitoring is about $1700.

This hardware will need to be put inside of a chassis.  The chassis will include opamps to condition the output detector signals, power supplies

# MPS System

We have designed and built a replacement for the legacy PLC-5 Rockwell Automation control system.  The upgrade has been designed to migrate the PLC-5 1771 hardware to ControlLogix 1756 using the Rockwell Automation conversion kit.  The system hardware has been assembled and the software has been written.  We still need to test the system with actual hardware and verify that it is functional.  There likely may be some modifications of the software that will be required.

## Interfaces

We will need to build an interface chassis that connects the MPS system to the rest of the RF system and to SPEAR3 as a whole.  It will have several inputs, both from within the RF system – the LLRF, the HVPS controller, another custom module that will detect some RF powers and generate a fault if the measured RF powers are exceeded, and possibly some optical arc detectors (Microstep-MIS) – and external faults from SPEAR3 such as SPEAR3 MPS, orbit interlock, and other as yet undefined permits.

## Optical Arc Detectors

I received a quote from Erik Bystricky from Microstep-MIS in November, 2024.  Each cavity requires two optical sensors, one each on the air side of the window and one each on the vacuum side of the window.  There are also ports to view the circulator and one on the air side of the klystron window.  (I don’t know how easy it will be to monitor the klystron window with a Microstep sensor.)  Each sensor then couples into a receiver, which can handle two sensors.  The cost for these devices, in Euros, are:

- Sensor:  470€  4700€

- Receiver:  635€  3175€

- 2m Interconnecting cable:  186€  930€

- DB25 cables:  $20  $200

Total materials about $10k

Will also need to make adapters, $2k design time and $500 each, for another $7k.  Estimate of $20k total.

### Inputs

- One electrical input from LLRF9 to an optocoupler

- One fiber optic input from the HVPS controller

- One summary electrical input from the RF power detector to an optocoupler

- One summary electrical input from Microstep-MIS Wave Arc Detector (optical arc detectors) to an optocoupler

- One 24 VDC input from the SPEAR3 MPS to an optocoupler

- One 24 VDC input from the SPEAR3 orbit interlock to an optocoupler

- Two spare inputs to an optocouplers

### Outputs

- One electrical output to the LLRF9 to tell it to disable its output

- One fiber optic output to the HVPS controller to enable the phase control thyristors

- One fiber optic output to the HVPS controller to prevent the MPS system from firing the crowbar thyristors

# HVPS Controller

## Upgrade Tasks

- Reverse engineer code for programmable logic controller (PLC) of Rockwell Automation SLC-500 (ML)

- Write code for Rockwell Automation CompactLogix controller (ML)

- Work with controls to complete interface between CompactLogix and EPICS (ML, SC)

- Design CompactLogix hardware system to replace SLC-500 hardware (ML)

- Modify PPS interface to meet current standards (ML, JS, MC)

- Specify power supplies required in upgraded controller (ML, JS)

- Specify any modifications to layout in upgraded controller (ML)

- Verify existing documentation of controller and HVPS interfaces (ML, JS)

- Document existing analog controller architecture (JS)

- Upgrade to new Enerpro controller (JS)

  - June 2022 cost estimate of $722 each for five boards or $3610 for all five.  Estimate $4000.

- Design new regulator and interface boards (JS)

- Layout, fabricate, and test new regulator and interface boards (?)

- Troubleshoot and repair three broken windings in HVPS1 (ML, SJ)

- Build test stand with new hardware (ML)

- Test new design in test lab (ML, JS, JE)

- Build two new controllers for HVPS1 and HVPS2 (ML)

- Complete documentation (ML, ?)

## Allen-Bradley RA Compact Logix 5000 PLC Purchases Required

| Description | Part Number | Price Each | Quantity | Total Price |
| --- | --- | --- | --- | --- |
| 18 spring RTB | AB 5069-RTB18-SPRING | 62.429 | 25 | 1560.72 |
| Output module | AB 5069-OF8 | 1535.638 | 3 | 4606.91 |
| Isolated relay output module | AB 5069-OX41 | 451.594 | 10 | 4515.94 |
| Universal analog input module | AB 5069-IY4 | 521.311 | 2 | 1042.62 |
| Analog input module | AB 5069-IF8 | 875.927 | 2 | 1751.85 |
| DC input module | AB 5069-IB16 | 265.706 | 4 | 1062.82 |
| 2MB Ethernet controller | AB 5069-L320ER | 3692.261 | 2 | 7384.52 |
| Spring RTB | AB 5069-RTB-64-SPRING | 34.151 | 2 | 68.30 |
| Total cost |  |  |  | 21993.68 |

## Maintenance Tasks (Not part of the upgrade project but included here for downtime schedule purposes)

- Replace oil pump in HVPS1 (SJ) (Replace oil pump in HVPS2 at next opportunity)

- Replace phase control thyristor stacks (SJ)

- Replace crowbar stacks (SJ)

## Interfaces

There will be software and hardware interfaces for this system.  The software interfaces will be between CompactLogix and EPICS.  The PLC will report back all of its analog data and digital status.  It will receive software instructions to

- Open/close the 12.47 kV contactor

- Enable the power supply to turn on (remove Enerpro fast and slow inhibits)

- Supply an output voltage set point at a rate no faster than 1 Hz.

There will also be a hardware interface between the HVPS PLC and the MPS controller for the RF system.  (There needs to be no direct hardware communication between the HVPS controller and LLRF9).

### Inputs

- Fiber optic permit that says MPS does not want to fire the output filter crowbar thyristors.

- Fiber optic permit that allows the phase control thyristors to fire.

### Output

- Fiber optic permit that tells the MPS that the HVPS controller is ready to turn on the phase control thyristors and ready to output high voltage.